## Sheet1
When: 03/06/2021 09:00 AM |  | Who: Group34 | Application: GitHub
Note: please make sure you fill all information related to your project below and convert/include link to Wiki Or readme.md (GitHub)
ID | Scenario Title | Status | Scenario | Remarks
1 | Startup page | Failed | Program startup, when Parkmate app launched - the menu should be clear and consistent | The time and the banner looks a bit confusing as there are two times given
2 | Startup page notification | Pass | When the app is running, a notification will pop-up asking users for permission. | The notification is clearly shown on the mobile app, asking whether users can accept to share their location or not.
3 | Given the user is logged in | Failed | The website cannot be opeded well | The Internet network is poor when logging in the website which doesn't from China
4 | Given the user is logged in | Pass | The page can be shown easily | It's easy to get all informations when we want to.
5 | When the user click on 'my account' | Failed | It's hard to log in well and get our information | The website crashes or the Internet connection has some problems
6 | When the user click on 'my account' | Pass | There are some profiles or blanks you don't know how to deal with | You can fill the information by the help of other users' preferences.
7 | Then a popup screen to edit account details is displayed | Failed | The account details cannot be edited well | Reconnect the Internet and try again in order to get the necessarily informations
8 | Then a popup screen to edit account details is displayed | Pass | Web pages can save user profiles in time and it's easy to open the right page | Display the contents that the user changed correctly in the configuration file
9
10
11
12
13
14
15