## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Group 34 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead | Colin | Mark | David | Leslie
Project Start Date: | 2021-09-14 |  |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling Increment: | 0 | time axis 2021-09-14 to 2021-11-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-09-14 to 2021-11-08
Iteration 01
Iteration planning and meeting | Goal | Colin | 25% | 2021-09-14 | 1 | 2021-09-14: 2
Complete stakehlder regist | High Risk | Mark | 100% | 2021-09-15 | 5
Design persona | Low Risk | David | 50% | 2021-09-16 | 10
Review and test persona | Med Risk | Leslie | 75% | 2021-09-24 | 4
Complete progress report | On Track | Colin | 100% | 2021-09-28 | 2
Milestone 01 | Milestone |  | 10% | 2021-10-01 | 1 | bar: 2021-10-01
Iteration 02
Iteration planning and meeting | Goal | Mark | 25% | 2021-10-03 | 13 | 2021-10-03: 2; 2021-10-04: 2; 2021-10-05: 2; 2021-10-06: 2; 2021-10-07: 2; 2021-10-08: 2; 2021-10-09: 2; 2021-10-10: 2; 2021-10-11: 2; 2021-10-12: 2; 2021-10-13: 2; 2021-10-14: 2; 2021-10-15: 2
Iteration planning and meeting | Med Risk | Colin | 50% | 2021-10-06 | 9
Record this information into GitHub boards. | Low Risk | David | 90% | 2021-10-08 | 11
Complete a Resource Requirement List for the Project. | High Risk | Leslie | 10% | 2021-10-11 | 1
Test the uploaded file and record any issues on GitHub. | Med Risk | Colin | 40% | 2021-10-14 | 24
Milestone 02 | Milestone | Mark | 10% | 2021-10-16 | 1
Iteration 03
Iteration planning and meeting | On Track | Leslie | 10% | 2021-09-29 | 4
collect information | Med Risk | David | 26% | 2021-10-02 | 14
creat chat | On Track | Colin | 45% | 2021-10-17 | 6
Record this information into GitHub boards. | Goal | Mark | 100% | 2021-11-02 | 3 | 2021-11-02: 2; 2021-11-03: 2; 2021-11-04: 2
sum data | Low Risk | David | 20% | 2021-10-01 | 19
Formulas:
Leslie = [Leslie, row above]+3

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-14 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 1 | time axis 2021-11-15 to 2022-01-09
Milestone description | Category | Assigned to | Progress | Start | Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-14 | 3 | M: 2; T: 2
Task 2 | Milestone |  |  | 2021-11-19 | 1 | bar: F
Task 3 | Low Risk |  | 50% | 2021-11-11 | 10
Task 4 | Milestone |  |  | 2021-12-04 | 1 | bar: S
Task 5 | Med Risk |  | 10% | 2021-11-20 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-20 | 13
Task 2 | On Track |  | 50% | 2021-11-22 | 9
Task 3 | Low Risk |  | 33% | 2021-11-27 | 11
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: M
Task 5 |  |  |  | 2021-11-30 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-29 | 4
Task 2 | Med Risk |  |  | 2021-12-02 | 14
Task 3 | On Track |  |  | 2021-12-17 | 6
Task 4 | Goal |  |  | 2021-12-21 | 3 | T: 2; W: 2; T: 2
Task 5 | Low Risk |  |  | 2021-11-20 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-24 | 15
Task 2 |  |  |  | 2022-01-07 | 5
Task 3 | Milestone |  |  | 2022-02-18 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-11-14 |  |  |  |  | November | [13 empty] | December | [34 empty] | January
Scrolling Increment: | 5 | time axis 2021-11-19 to 2022-01-13
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-11-19 to 2022-01-13
TITLE 1
Task 1 | Goal | Name | 25% | 2021-11-14 | 3
Task 2 | Milestone |  |  | 2021-11-19 | 1 | bar: 2021-11-19
Task 3 | Low Risk |  | 50% | 2021-11-11 | 10
Task 4 | Milestone |  |  | 2021-12-04 | 1 | bar: 2021-12-04
Task 5 | Med Risk |  | 10% | 2021-11-20 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-11-20 | 13
Task 2 | On Track |  | 50% | 2021-11-22 | 9
Task 3 | Low Risk |  | 33% | 2021-11-27 | 11
Task 4 | Milestone |  |  | 2021-11-29 | 1 | bar: 2021-11-29
Task 5 |  |  |  | 2021-11-30 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-11-29 | 4
Task 2 | Med Risk |  |  | 2021-12-02 | 14
Task 3 | On Track |  |  | 2021-12-17 | 6
Task 4 | Goal |  |  | 2021-12-21 | 3 | 2021-12-21: 2; 2021-12-22: 2; 2021-12-23: 2
Task 5 | Low Risk |  |  | 2021-11-20 | 19
TITLE 4
Task 1 |  |  |  | 2021-12-24 | 15
Task 2 |  |  |  | 2022-01-07 | 5
Task 3 | Milestone |  |  | 2022-02-18 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one